## 28Feb23
Date | 2023-02-28
venue | Teams
Attendance
Sonia | y
Narinder | y
Godswill | y
Gideon PM | y
Ozomata | y
Item | Status | owner | Comment | Deadline | Status by next meeting
We introduced ourselves as this was the 1st meeting.
Gideon was the Project Manager for today’s meeting.
We introduced ourselves as this was the 1st meeting. Gideon was the Project Manager for today’s meeting. A Github Repository was created, and all members received an invitation to join. The expectation is for everyone to share processes along the way and monitor progress (we shouldn’t wait till the deadline before committing). https://github.com/gideonclottey/Bank-App.git
We reviewed the assessment/CRG to have a better understanding of the task at hand.
To ensure we follow agile processes short tasks have been assigned to all members using the We made use of the our Github Kanban (repository Project) to assign tasks.
To enable agile meetings, groups and workspaces were created on MS teams and slack respectively
To DO
Godswill was assigned to draft the user stories and share with Team members - | Open |  |  | 2023-02-28
Ozomata and Narinder to come up with the wireframe design, dependent on (1) above | open |  |  | TBD
Stand-up meeting to be held via Teams on 21/02/2023 by 12:00pm, Ozomata was assigned the Project Manager for the day with discussions to be centered around reviewing the user stories. |  |  |  | 2023-03-01

## 01Mar23
Date | 2023-03-01
venue | Teams
Attendance
Sonia | Y
Narinder | Y
Godswill | Y
Gideon | Y
Ozomata (PM) | Y
Item | Status | owner | Comment | Deadline | Status by next meeting
Meeting Shedules (30-60 mins)
Minutes Suggestions Excel vs Other tools |  | PM for the day | keep the excel for now.
finalise User story and meeting minutes and commit | Closed | Godswill and Oz | PM must commit the minutes of the day Update Readme with User story |  | Task Concluded, commit has been made
feedback on mockup -Narinder and Ozomata | open | Narinder &Oz | addintional task create logo | 2023-03-02
User acceptance criteria- Assignment and time line | open | Gideon &Sonia | MVP to be ready on or befor 21st March | 2023-03-06
Gannt chart creation -Assignment and timeline | open | oz |  | 2023-03-02
overview of all tools (python, django,UI UX tools Figma , PM tools (Teams,Slag,Git kanban, GanntProject) |  |  | 20X20X20 rule to be informed
Design stage |  |  | Dependent on Next meeting outcomes
AOB |  | Gideon | Stick to deadlines and be prepared
Next meeting |  | oz | INB 1102 | 2023-03-04

## 04Mar23
Date | 2023-03-04
venue | Teams
Attendance
Sonia | Y
Narinder | Y
Godswill | Y
Gideon | Y
Ozomata (PM) | Y
Item | Status | owner | Comment | Deadline | Status by next meeting
Meeting Shedules (30-60 mins) |  |  | i. It was suggested that we make our meeting physical so as to cover more ground and meet with deadline for MVP, this was accepted by all. ii. It was suggested that meeting be held 2-3 times weekly till project completion.
Minutes Suggestions Excel vs Other tools |  | PM for the day | keep the excel for now.
feedback on mockup -Narinder and Ozomata | Closed | Narinder &Oz | addintional task create logo | 2023-03-02 | i. Mockup design was presented to Customer for review and it was accepted. ii. Customer requested for an appropriate logo and relevant bank name.
User acceptance criteria- Assignment and time line | open | Gideon &Sonia | MVP to be ready on or befor 21st March | 2023-03-06
Gannt chart creation -Assignment and timeline | Closed | oz |  | 2023-03-02 | Task completed, team reviewed and was satisfied
overview of all tools (python, django,UI UX tools Figma , PM tools (Teams,Slag,Git kanban, GanntProject) |  |  | 20X20X20 rule to be informed |  | An explanation of all the tools was made by Gideon & Narinder, it was clear at the end of the day while they are essential for our task
Frontend Design of the banking application | open | Narinder &Oz | Replicate mockup design to front end using HTML, CSS & JS | 2023-03-10
AOB |  | Gideon | Stick to deadlines and be prepared
Next meeting |  |  | INB 1102 | 2023-03-10

## 10Mar23
Date | 2023-03-10
venue | Teams
Attendance
Sonia (PM) | Y
Narinder | Y
Godswill | Y
Gideon | Y
Ozomata | Y
Item | Status | owner | Comment | Deadline | Status by next meeting
Minutes Suggestions Excel vs Other tools |  | PM for the day | keep the excel for now.
Bank Name & Logo Design | Closed | Narinder &Oz | Team came up with a list of bank names to be presented to the customer | 2023-03-10 | i. Customer accepted the bank name and logo provided but made few edit to the logo color. He appreciated the effort of the team.
User acceptance criteria- Assignment and time line | Closed | Gideon &Sonia | MVP to be ready on or befor 21st March | 2023-03-06 | i. User acceptance criteria was reviewed and accepted with minor edits made. ii. Commit was made to github repository.
Frontend Design of the banking application | open | Narinder &Oz | Replicate mockup design to front end using HTML, CSS & JS | 2023-03-10 | i. Narinder & OZ presented the front-end design template to the customer. ii. Customer appreciated the team's efforts but pointed out changes to be made, this is shown below
AOB | open |  | Based on customer feedback, it was suggested that proper review to be done on the frontend design before commencement of Backend | 2023-03-13
Next meeting |  |  | INB 1301 | 2023-03-13
Customer Feedback for the Frontend Design
i. The user interface lacked consistency in terms of design elements such as color, typography and layout. This can make the application look disjointed and confusing for the user.
ii. Some of the design choices may not align with the user's needs and expectations. For example, some of the buttons and menus are not easily discoverable and important information such as account balances are not prominently displayed.
iii. Lastly, I feel the overall design could benefit from more visual hierarchy to guide the user's attention to the most important information and actions. This I believe can be achieved through the use of appropriate sizing, contrast and visual cues.

## 13Mar23
Date | 2023-03-13
venue | Teams
Attendance
Sonia | Y
Narinder (PM) | Y
Godswill | Y
Gideon | Y
Ozomata | Y
Item | Status | owner | Comment | Deadline | Status by next meeting
Minutes Suggestions Excel vs Other tools |  | PM for the day | keep the excel for now.
Frontend Design of the banking application | Closed | Narinder &Oz | Replicate mockup design to front end using HTML, CSS & JS | 2023-03-10 | i. Customer reviewed changes made to the front-end template based on previous feedback and provided comments below.
Backend Design | open | Gideon & Godswill | i. Gideon was placed as the proponent/'Big Boss' to lead the team on this ii. He delegated task to team members, explained the tools/framework to be used (Django). iii. Team members were assigned a task to do at the backend to ensure everyone participated in the activity. | 2023-03-18
Design of the structural and behavioural diagrams | open | Sonia, Narinder & OZ | Based on the scope of our project, the following diagrams were suggested for designs: class, sequence, entity-relationship and use-case diagram | 2023-03-18
Testing | open | Godswill & OZ |  | 2023-03-20
MVP Release (V 1.0) | open |  |  | 2023-03-20
AOB | open |  |  | 2023-03-20
Next meeting |  |  | INB 1102 | 2023-03-20
Customer Feedback for the Frontend Design
i. Customer commended the team on the excellent work they have done in incorporating previous feedback on the front-end design of the project. He mentioned that the changes made have greatly improved the user experience, and he appreciated the team's dedication to creating a high quality product.
ii. There were few areas where we could further enhance the design. For example, the color scheme could be adjusted to provide better contrast and make important elements stand out more. Additionally, some o the font sizes could be increased to improve readability.
iii. Overall, customer was impressed with the team's effort and appreciated the responsiveness to feedback provided. He is confident that the team would create a user-friendly and effective product.

## 19Mar23
Date | 2023-03-19
venue | Teams
Attendance
Sonia | Y
Narinder | Y
Godswill | Y
Gideon (PM) | Y
Ozomata | Y
Item | Status | owner | Comment | Deadline | Status by next meeting
Minutes Suggestions Excel vs Other tools |  | PM for the day | keep the excel for now.
Backend Design | Closed | Gideon & Godswill | i. Gideon was placed as the proponent/'Big Boss' to lead the team on this ii. He delegated task to team members, explained the tools/framework to be used (Django). iii. Team members were assigned a task to do at the backend to ensure everyone participated in the activity. | 2023-03-18 | i. The team reported with their feedback, errors were spotted through pair programming and feedback provided. ii. Commit was made to github repository
Design of the structural and behavioural diagrams | Closed | Sonia, Narinder & OZ | Based on the scope of our project, the following diagrams were suggested for designs: class, sequence, entity-relationship and use-case diagram | 2023-03-18 | i. The team reported with update on the system designs and constructive feedback were provided.
Testing | open | Godswill & OZ |  | 2023-03-20
MVP Release (V 1.0) | open |  |  | 2023-03-20
AOB | open |  |  | 2023-03-20
Next meeting |  |  | INB 1102 | 2023-03-20